## Sheet1
ICS SUMMATIVE PROJECT - GANTT CHART
| Phase | Est. Start Date | Est. Finish Date | Name | Description
| 1 | June 1 2013 | June 5 2013 | Scope Plan && GANT Chart | The scope plan describes the objectives of the project and the GANTT creates a managing plan
| 2 | June 6 2013 | June 10 2013 | UML Class Diagram | This consisted of the main planning phase of the project. Creation of required classes (like Map, etc) as well as decisions regarding the life forms (their interactions and appearances) ocurred.
| 3 | June 10 2013 | June 11 2013 | Demo | Simple drawing of maps and random population.
| 4 | June 12 2013 | June 16 2013 | Completion of program | Program completed.
| 5 | June 16 2013 | June 17 2013 | Testing | Testing. Fixed/Redesigned the image loading, etc.
| 6 | June 16 2013 | June 17 2013 | User Documentation Guide | A document describing the life forms and their characteristics, as well as how the user may actually use the program.